## Employee Task
Dept and Team | Task Owner | QA | Reviewer | Requirement Collector | Project Name | Parent Task | Task No | Task Name | Task Status | Planned Start | Planned End | Actual Start | Actual End | Dev Over Due Days | QAT Over Due Days | Over Due Days | Planned Mandays | Actual Mandays | Planned Progress | Actual Progress | Difference | Dev Workload | Qat Workload | Task Type
| Arkar Zin Naing | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Sprint 3 (5 Weeks - Dev + User Review) | TN20230928-17302 | Native UI: Cus List , details, task, taks list, task note, task note list, note, note list UI | Assign | 2023-Sep-28 | 2023-Oct-03 |  |  | 0 | 0 | 64 | 6 | 0 | 100.00 | 0 | 100.00 | 2 | 1 | task
| Arkar Zin Naing | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Sprint 3 (5 Weeks - Dev + User Review) | TN20231006-17415 | Native UI: customer search, filter and sorting | Assign | 2023-Oct-06 | 2023-Oct-10 |  |  | 0 | 0 | 57 | 5 | 0 | 100.00 | 0 | 100.00 | 1 | 1 | task
| Arkar Zin Naing | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Sprint 3 (5 Weeks - Dev + User Review) | TN20231009-17449 | Native UI: Module's Filter and Sorting | Assign | 2023-Oct-09 | 2023-Oct-13 |  |  | 0 | 0 | 54 | 5 | 0 | 100.00 | 0 | 100.00 | 2 | 2 | task
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Sprint 3 (5 Weeks - Dev + User Review) | TN20231009-17451 | Proposal: Sign (Upload + Download) API Integration | Development | 2023-Oct-09 | 2023-Oct-12 | 2023-Oct-23 |  | 44 | 0 | 55 | 4 | 0 | 100.00 | 70 | 30.00 | 2 | 1 | task
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Sprint 3 (5 Weeks - Dev + User Review) | TN20231012-17493 | Native UI: Proposal sign+attchment API issue fix | Assign | 2023-Oct-11 | 2023-Oct-18 |  |  | 0 | 0 | 49 | 8 | 0 | 100.00 | 0 | 100.00 | 3 | 1 | issue
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Proposal Module | TN20231024-17637 | Proposal: Life Pro > Sign > Betel, | Assign | 2023-Oct-23 | 2023-Nov-02 |  |  | 0 | 0 | 34 | 11 | 0 | 100.00 | 0 | 100.00 | 6 | 2 | task
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Proposal Module | TN20231023-17607 | Life Pro: Sign > Betel, Contingent, Agent Confidential, 3rd party payor | Assign | 2023-Oct-23 | 2023-Oct-31 |  |  | 0 | 0 | 36 | 9 | 0 | 100.00 | 0 | 100.00 | 5 | 1 | task
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Proposal Module | TN20231023-17608 | Proposal > Sign Validation | Assign | 2023-Oct-30 | 2023-Nov-02 |  |  | 0 | 0 | 34 | 4 | 0 | 100.00 | 0 | 100.00 | 2 | 1 | task
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Issue | TN20231031-17710 | Proposal > Sign > Life Pro validation | Development | 2023-Nov-01 | 2023-Nov-07 | 2023-Nov-02 |  | 33 | 0 | 29 | 7 | 0 | 100.00 | 10 | 90.00 | 3 | 1 | issue
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Issue | TN20231103-17751 | Proposal: sign>contingent from+ declare > | Assign | 2023-Nov-02 | 2023-Nov-09 |  |  | 0 | 0 | 27 | 8 | 0 | 100.00 | 0 | 100.00 | 3 | 2 | issue
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Issue | TN20231104-17755 | Proposal: sign and declare page question forms issue fix | Assign | 2023-Nov-04 | 2023-Nov-09 |  |  | 0 | 0 | 27 | 6 | 0 | 100.00 | 0 | 100.00 | 2 | 1 | issue
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Sprint 4 (6 Weeks - Dev + User Review) | TN20231106-17767 | Multi Select function for questionnaire form | Assign | 2023-Nov-06 | 2023-Nov-09 |  |  | 0 | 0 | 27 | 4 | 0 | 100.00 | 0 | 100.00 | 2 | 1 | task
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Issue | TN20231107-17799 | Declare: max rows issue fix | Assign | 2023-Nov-07 | 2023-Nov-13 |  |  | 0 | 0 | 23 | 7 | 0 | 100.00 | 0 | 100.00 | 3 | 1 | issue
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Health Care Product | TN20231108-17820 | multiple select issue fix and application form 5/6 data bind issue | Assign | 2023-Nov-08 | 2023-Nov-14 |  |  | 0 | 0 | 22 | 7 | 0 | 100.00 | 0 | 100.00 | 2 | 2 | issue
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Proposal Module | TN20231109-17845 | Adding signature to PDF Output file | Assign | 2023-Nov-09 | 2023-Nov-15 |  |  | 0 | 0 | 21 | 7 | 0 | 100.00 | 0 | 100.00 | 2 | 2 | task
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Issue | TN20231111-17889 | using camera for attachment | Assign | 2023-Nov-11 | 2023-Nov-15 |  |  | 0 | 0 | 21 | 5 | 0 | 100.00 | 0 | 100.00 | 0 | 1 | task
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Issue | TN20231113-17923 | plugin issue fix for camera photo upload | Assign | 2023-Nov-13 | 2023-Nov-15 |  |  | 0 | 0 | 21 | 3 | 0 | 100.00 | 0 | 100.00 | 1 | 1 | issue
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Issue | TN20231113-17924 | Timebomb development | Assign | 2023-Nov-14 | 2023-Nov-22 |  |  | 0 | 0 | 14 | 9 | 0 | 100.00 | 0 | 100.00 | 4 | 2 | task
| Aung Kyaw Myo | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Sprint 4 (6 Weeks - Dev + User Review) | TN20231109-17850 | Data Sync | Assign | 2023-Nov-16 | 2023-Nov-29 |  |  | 0 | 0 | 7 | 14 | 0 | 100.00 | 0 | 100.00 | 6 | 3 | task
BCS 2 | Cynthia Nyein | Aye Myat Hnin | Kaung Htet Kyaw | Kaung Htet Kyaw | Anastas XBITU | Transition Stage | TN20231128-18103 | Support Anastas Production Test and Prepare API Document | Development | 2023-Nov-28 | 2023-Dec-08 | 2023-Nov-28 |  | 0 | 0 | 0 | 9 | 0 | 81.82 | 80 | 1.82 | 9 | 1 | ba_task
ERP | Kaung Myat Soe | May Lwin Khaing | Kaung Htet Kyaw | Kaung Htet Kyaw | New GLPI | Sprint 2 Development | TN20231123-18078 | Develop Production order feedback from GLPI | Task Complete | 2023-Nov-23 | 2023-Dec-05 | 2023-Nov-23 |  | 0 | 0 | 1 | 5 | 0 | 100.00 | 90 | 10.00 | 7 | 2 | task
ERP | Kaung Myat Soe | May Lwin Khaing | Kaung Htet Kyaw | Kaung Htet Kyaw | New GLPI | Sprint 2 Development | TN20231123-18079 | Develop Product "On Hand" issue and Add Set to Draft in GRN | Task Complete | 2023-Nov-29 | 2023-Dec-05 | 2023-Nov-28 |  | 0 | 0 | 1 | 3 | 0 | 100.00 | 90 | 10.00 | 3 | 2 | task
ERP | Kaung Myat Soe | May Lwin Khaing | Kaung Htet Kyaw | Kaung Htet Kyaw | New GLPI | Sprint 2 Development | TN20231205-18228 | Develop Cash Flow Statement Report | Development | 2023-Dec-05 | 2023-Dec-11 | 2023-Dec-05 |  | 0 | 0 | 0 | 5 | 0 | 28.57 | 30 | -1.43 | 4 | 1 | task
ERP | Su Darly | May Lwin Khaing | Kaung Htet Kyaw | Kaung Htet Kyaw | New GLPI | Sprint 2 Development | TN20231123-18081 | Develop Sprint 1 feedback for contract, Transfer and GRN entries | Done | 2023-Nov-27 | 2023-Nov-30 | 2023-Nov-28 | 2023-Nov-30 | 0 | 0 | 0 | 4 | 3 | 100.00 | 100 | 0.00 | 3 | 1 | task
ERP | Su Darly | May Lwin Khaing | Kaung Htet Kyaw | Kaung Htet Kyaw | New GLPI | Sprint 2 Development | TN20231123-18082 | Carry PO amount in Advance and add % field to get advance amount | Task Complete | 2023-Nov-30 | 2023-Dec-04 | 2023-Nov-30 |  | 0 | 0 | 2 | 3 | 0 | 100.00 | 90 | 10.00 | 2 | 1 | task
ERP | Su Darly | May Lwin Khaing | Kaung Htet Kyaw | Kaung Htet Kyaw | New GLPI | Sprint 2 Development | TN20231123-18080 | Add bill amount and percentage field in register payment | Task Complete | 2023-Dec-01 | 2023-Dec-04 | 2023-Nov-30 |  | 0 | 0 | 2 | 2 | 0 | 100.00 | 90 | 10.00 | 1 | 1 | task
ERP | Su Darly | Aye Myat Hnin | Than Htoo Aung | Ei Than Thar | DGB-MFI SYSTEM-MA-2023.06.01 | MFI System-Maintenance | TN20231201-18194 | MIS Report - Wrong Staff Information for October 2023 [RI-000101] | Task Complete | 2023-Dec-04 | 2023-Dec-06 | 2023-Dec-04 |  | 0 | 0 | 0 | 3 | 0 | 100.00 | 90 | 10.00 | 2 | 1 | task
ERP | Su Darly | May Lwin Khaing | Kaung Htet Kyaw | Kaung Htet Kyaw | New GLPI | Sprint 2 Development | TN20231205-18230 | Develop Advance Payment Report | Assign | 2023-Dec-05 | 2023-Dec-11 |  |  | 0 | 0 | 0 | 5 | 0 | 28.57 | 0 | 28.57 | 4 | 1 | task
Infra | Aung Myo Thu | Nwe Yi Win | Than Htoo Aung | Sei Thu Win | KBZMS-DFE SYSTEM-MA-2023.02.01 | KBZMS-DFE SYSTEM-MAINTENANCE | TN20231130-18169 | Check KBZMS DFE App 2 Server Availability | Done | 2023-Nov-30 | 2023-Dec-04 | 2023-Nov-30 | 2023-Dec-01 | 0 | 0 | 0 | 3 | 3 | 100.00 | 100 | 0.00 | 2 | 1 | task
Java | Hein Win Naing | Nwe Yi Win | Than Htoo Aung | Sei Thu Win | KBZMS-DFE SYSTEM-MA-2023.02.01 | KBZMS-DFE SYSTEM-MAINTENANCE | TN20231123-18077 | Write audit log of failed file attachment to TCS sFTP server | Done | 2023-Nov-23 | 2023-Nov-28 | 2023-Nov-23 | 2023-Nov-29 | 0 | 0 | 1 | 4 | 4 | 100.00 | 100 | 0.00 | 2 | 2 | task
Java | Hein Win Naing | Nwe Yi Win | Sei Thu Win | Sei Thu Win | KACE: KBZMS Automated Claims Essential | Sprint 1 (4W Development + 1W UT) | TN20231201-18187 | SVR-01L/F : Surveyor Listing and Detail Form | Development | 2023-Dec-04 | 2023-Dec-13 | 2023-Dec-04 |  | 0 | 0 | 0 | 8 | 0 | 30.00 | 40 | -10.00 | 5 | 2 | task
Java | Kaung Thu Lin | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Edu Goal Product | TN20231120-18042 | Health Care data binding checking from quotation to proposal submission | Done | 2023-Nov-20 | 2023-Nov-24 | 2023-Nov-20 | 2023-Nov-29 | 0 | 0 | 5 | 5 | 8 | 100.00 | 100 | 0.00 | 2 | 2 | task
Java | Kaung Thu Lin | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Sprint 4 (6 Weeks - Dev + User Review) | TN20231121-18053 | Health Care Sales Illustration PDF file | Done | 2023-Nov-21 | 2023-Nov-28 | 2023-Nov-21 | 2023-Nov-29 | 0 | 0 | 1 | 6 | 7 | 100.00 | 100 | 0.00 | 3 | 1 | task
Java | Kaung Thu Lin | May Lwin Khaing | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Health Care Product | TN20231124-18096 | Health Care Application Form PDF | Done | 2023-Nov-24 | 2023-Dec-04 | 2023-Nov-28 | 2023-Dec-04 | 0 | 0 | 0 | 5 | 5 | 100.00 | 100 | 0.00 | 4 | 1 | task
Java | Kaung Thu Lin | May Lwin Khaing | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Health Care Product | TN20231130-18176 | health care application form pdf data binding | Done | 2023-Nov-30 | 2023-Dec-05 | 2023-Nov-30 | 2023-Dec-04 | 0 | 0 | 0 | 4 | 3 | 100.00 | 100 | 0.00 | 2 | 1 | task
Java | Kaung Thu Lin | May Lwin Khaing | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Proposal Module | TN20231204-18224 | health care data bind + PDF part 7 add | QAT | 2023-Dec-04 | 2023-Dec-08 | 2023-Dec-04 |  | 0 | 0 | 0 | 5 | 2 | 60.00 | 80 | -20.00 | 2 | 1 | task
Java | Khant Zin Win | Aye Myat Hnin | Hnin Pwint Phyu Khine | Hnin Pwint Phyu Khine | IBK CAPITAL-MFI SYSTEM-MA-2023.02.09 | MIFOS SYSTEM-MAINTENANCE | TN20231128-18117 | To check Holiday Scheduler is taking too long to finish | Done | 2023-Nov-28 | 2023-Nov-30 | 2023-Nov-28 | 2023-Nov-30 | 0 | 0 | 0 | 3 | 3 | 100.00 | 100 | 0.00 | 2 | 1 | issue
Java | Khant Zin Win | May Lwin Khaing | Than Htoo Aung | Ei Than Thar | IBK CAPITAL-MFI SYSTEM-MA-2023.02.09 | ERP SYSTEM-MAINTENANCE | TN20231130-18170 | Foreclosure Loan - wrong close account [UR-000085] | Done | 2023-Nov-30 | 2023-Dec-01 | 2023-Nov-30 | 2023-Dec-01 | 0 | 0 | 0 | 2 | 2 | 100.00 | 100 | 0.00 | 1 | 1 | task
Java | Khant Zin Win | Aye Myat Hnin | Hnin Pwint Phyu Khine | Hnin Pwint Phyu Khine | IBK CAPITAL-MFI SYSTEM-MA-2023.02.09 | MIFOS SYSTEM-MAINTENANCE | TN20231130-18174 | To count loan cycle for every products | Task Complete | 2023-Dec-01 | 2023-Dec-05 | 2023-Dec-01 |  | 0 | 0 | 1 | 3 | 0 | 100.00 | 90 | 10.00 | 2 | 1 | issue
Java | Khant Zin Win | Aye Myat Hnin | Than Htoo Aung | Hnin Ei Ei Hlaing | IBK CAPITAL-MFI SYSTEM-MA-2023.02.09 | ERP SYSTEM-MAINTENANCE | TN20231205-18235 | Loan Schedule date error - No skip of holiday plan in loan schedule [TS-000514] | Task Complete | 2023-Dec-05 | 2023-Dec-06 | 2023-Dec-05 |  | 0 | 0 | 0 | 2 | 0 | 100.00 | 90 | 10.00 | 1 | 1 | task
Java | Sandar Linn | Nwe Yi Win | Than Htoo Aung | Sei Thu Win | KBZMS-DFE SYSTEM-MA-2023.02.01 | KBZMS-DFE SYSTEM-MAINTENANCE | TN20231123-18087 | Change Report To Name in Management Portal [Production] | Done | 2023-Nov-24 | 2023-Nov-28 | 2023-Nov-24 | 2023-Nov-29 | 0 | 0 | 1 | 3 | 3 | 100.00 | 100 | 0.00 | 1 | 2 | task
Java | Sandar Linn | Aye Myat Hnin | Kaung Htet Kyaw | Kaung Htet Kyaw | Anastas XBITU | New Requirement develop requested from Training Session | TN20231128-18104 | Develop Multi Devices Process for login (Email verify) | Task Complete | 2023-Nov-28 | 2023-Dec-04 | 2023-Nov-28 |  | 0 | 0 | 2 | 5 | 0 | 100.00 | 90 | 10.00 | 4 | 1 | task
Java | Sandar Linn | Aye Myat Hnin | Kaung Htet Kyaw | Kaung Htet Kyaw | Anastas XBITU | New Requirement develop requested from Training Session | TN20231204-18203 | Develop new device request process | Development | 2023-Dec-04 | 2023-Dec-11 | 2023-Dec-04 |  | 0 | 0 | 0 | 6 | 0 | 37.50 | 25 | 12.50 | 5 | 1 | task
Java | Shwe Yee Myint | Aye Myat Hnin | Kaung Htet Kyaw | Kaung Htet Kyaw | Anastas XBITU | New Requirement develop requested from Training Session | TN20231128-18122 | add schedular for card balance update in every 10 mins | Done | 2023-Nov-28 | 2023-Nov-29 | 2023-Nov-28 | 2023-Nov-29 | 0 | 0 | 0 | 2 | 2 | 100.00 | 100 | 0.00 | 1 | 1 | task
Java | Shwe Yee Myint | Aye Myat Hnin | Kaung Htet Kyaw | Kaung Htet Kyaw | Anastas XBITU | New Requirement develop requested from Training Session | TN20231129-18155 | Fix Auto rerun in topup and refund, and fix issue in audit log | Done | 2023-Nov-29 | 2023-Dec-01 | 2023-Nov-29 | 2023-Dec-01 | 0 | 0 | 0 | 3 | 3 | 100.00 | 100 | 0.00 | 2 | 1 | task
Java | Shwe Yee Myint | Aye Myat Hnin | Kaung Htet Kyaw | Kaung Htet Kyaw | Anastas XBITU | New Requirement develop requested from Training Session | TN20231201-18183 | Sequence diagram for Staking process | Task Complete | 2023-Dec-01 | 2023-Dec-04 | 2023-Dec-01 |  | 0 | 0 | 2 | 2 | 0 | 100.00 | 90 | 10.00 | 1 | 1 | task
Java | Shwe Yee Myint | Aye Myat Hnin | Kaung Htet Kyaw | Kaung Htet Kyaw | Anastas XBITU | New Requirement develop requested from Training Session | TN20231204-18205 | Support Anastas Issues for Devices login | Development | 2023-Dec-04 | 2023-Dec-11 | 2023-Dec-04 |  | 0 | 0 | 0 | 6 | 0 | 37.50 | 25 | 12.50 | 5 | 1 | task
Java | Shwe Yee Myint | Aye Myat Hnin | Zin Min Thant | Zin Min Thant | Internal Java Unit 2023 | Internal Mifos Task | TN20231204-18209 | Merge EarlyDawn Demo Code to Mifos Standard Demo | QAT | 2023-Dec-04 | 2023-Dec-08 | 2023-Dec-05 |  | 0 | 0 | 0 | 3 | 0 | 60.00 | 80 | -20.00 | 2 | 3 | task
Java | Shwe Yee Myint | Aye Myat Hnin | Kaung Htet Kyaw | Kaung Htet Kyaw | Anastas XBITU | New Requirement develop requested from Training Session | TN20231205-18232 | Sequence Diagram of Fund and Deposit and api documentation preparation | Development | 2023-Dec-05 | 2023-Dec-13 | 2023-Dec-05 |  | 0 | 0 | 0 | 7 | 0 | 22.22 | 0 | 22.22 | 6 | 1 | task
Java | Soe Sandar Oo | Aye Myat Hnin | Than Htoo Aung | Ei Than Thar | DGB-MFI SYSTEM-MA-2023.06.01 | MFI System-Maintenance | TN20231128-18119 | Branch Collection Individual Report_Customer ID Not Enough Column Space [BS-000032] | Done | 2023-Nov-28 | 2023-Nov-29 | 2023-Nov-28 | 2023-Nov-29 | 0 | 0 | 0 | 2 | 2 | 100.00 | 100 | 0.00 | 1 | 1 | task
Java | Soe Sandar Oo | Aye Myat Hnin | Than Htoo Aung | Ei Than Thar | DGB-MFI SYSTEM-MA-2023.06.01 | MFI System-Maintenance | TN20231129-18156 | Branch Collection Group_All Parameter Report Downloading Data Issue [BS-000033] | Done | 2023-Nov-29 | 2023-Nov-30 | 2023-Nov-29 | 2023-Nov-30 | 0 | 0 | 0 | 2 | 2 | 100.00 | 100 | 0.00 | 1 | 1 | task
Java | Soe Sandar Oo | Aye Myat Hnin | Than Htoo Aung | Ei Than Thar | DGB-MFI SYSTEM-MA-2023.06.01 | MFI System-Maintenance | TN20231130-18181 | FRD Village Report_All Region Can't Download Issue [UR-000086] | Done | 2023-Nov-30 | 2023-Dec-01 | 2023-Nov-30 | 2023-Dec-01 | 0 | 0 | 0 | 2 | 2 | 100.00 | 100 | 0.00 | 1 | 1 | task
Java | Soe Sandar Oo | Aye Myat Hnin | Than Htoo Aung | Ei Than Thar | DGB-MFI SYSTEM-MA-2023.06.01 | MFI System-Maintenance | TN20231130-18167 | Saving Balance By Customer & Loans Listing Reports_To Change Customer Type [RI-000099] | Done | 2023-Nov-30 | 2023-Dec-01 | 2023-Nov-30 | 2023-Dec-01 | 0 | 0 | 0 | 2 | 2 | 100.00 | 100 | 0.00 | 1 | 1 | task
Java | Soe Sandar Oo | Aye Myat Hnin | Than Htoo Aung | Ei Than Thar | DGB-MFI SYSTEM-MA-2023.06.01 | MFI System-Maintenance | TN20231130-18175 | Client Report_Not Enough Space in customer ID column [RI-000100] | Done | 2023-Dec-01 | 2023-Dec-04 | 2023-Dec-01 | 2023-Dec-05 | 0 | 0 | 1 | 2 | 2 | 100.00 | 100 | 0.00 | 1 | 1 | task
Java | Soe Sandar Oo | Aye Myat Hnin | Than Htoo Aung | Ei Than Thar | DGB-MFI SYSTEM-MA-2023.06.01 | MFI System-Maintenance | TN20231204-18210 | Guarantor Duplicate Issue_Loan Disbursement By Customer Report [RI-000103] | Task Complete | 2023-Dec-04 | 2023-Dec-05 | 2023-Dec-04 |  | 0 | 0 | 1 | 2 | 0 | 100.00 | 90 | 10.00 | 1 | 1 | task
Java | Soe Thiha Kyaw | Nwe Yi Win | Than Htoo Aung | Ei Than Thar | KBZMS-DFE SYSTEM-MA-2023.02.01 | KBZMS-DFE SYSTEM-MAINTENANCE | TN20231129-18159 | Product name search filter didn't show the correct one [TS-000511] | Done | 2023-Nov-29 | 2023-Dec-04 | 2023-Nov-29 | 2023-Dec-01 | 0 | 0 | 0 | 4 | 4 | 100.00 | 100 | 0.00 | 3 | 1 | task
Java | Soe Thiha Kyaw | Nwe Yi Win | Than Htoo Aung | Ei Than Thar | KBZMS-DFE SYSTEM-MA-2023.02.01 | KBZMS-DFE SYSTEM-MAINTENANCE | TN20231205-18227 | Not existing user accounts appear on Dashboard [TS-000513] | Development | 2023-Dec-05 | 2023-Dec-08 | 2023-Dec-05 |  | 0 | 0 | 0 | 4 | 0 | 50.00 | 20 | 30.00 | 2 | 2 | task
Java | Thant Sin Aung | Nwe Yi Win | Than Htoo Aung | Sei Thu Win | KBZMS-DFE SYSTEM-MA-2023.02.01 | KBZMS-DFE SYSTEM-MAINTENANCE | TN20231123-18086 | KBZMS Customer Care iOS App Test Flight Deployment | Done | 2023-Nov-23 | 2023-Nov-28 | 2023-Nov-23 | 2023-Nov-29 | 0 | 0 | 1 | 4 | 4 | 100.00 | 100 | 0.00 | 1 | 3 | task
Java | Thant Sin Aung | Nwe Yi Win | Sei Thu Win | Sei Thu Win | KBZMS-DFE SYSTEM-MA-2023.02.01 | KBZMS-DFE SYSTEM-MAINTENANCE | TN20231128-18126 | Preparation and upload KRIS and Customer Care app into PlayStore and App Store | Done | 2023-Nov-28 | 2023-Nov-30 | 2023-Nov-28 | 2023-Nov-30 | 0 | 0 | 0 | 3 | 3 | 100.00 | 100 | 0.00 | 1 | 1 | task
Java | Thant Sin Aung | Nwe Yi Win | Sei Thu Win | Sei Thu Win | KACE: KBZMS Automated Claims Essential | Sprint 1 (4W Development + 1W UT) | TN20231201-18186 | USR-01F, ROL-01F : User and Role Management Detail | Development | 2023-Dec-04 | 2023-Dec-08 | 2023-Dec-05 |  | 0 | 0 | 0 | 5 | 0 | 60.00 | 50 | 10.00 | 3 | 2 | task
Java | Thant Sin Aung | Nwe Yi Win | Than Htoo Aung | Ei Than Thar | KBZMS-DFE SYSTEM-MA-2023.02.01 | KBZMS-DFE SYSTEM-MAINTENANCE | TN20231204-18200 | Can't generate two report in the management portal [TS-000512] | QAT Deployment | 2023-Dec-04 | 2023-Dec-05 | 2023-Dec-04 |  | 0 | 0 | 1 | 2 | 0 | 100.00 | 80 | 20.00 | 1 | 1 | task
Java | Thant Sin Aung | Nwe Yi Win | Sei Thu Win | Sei Thu Win | KACE: KBZMS Automated Claims Essential | Sprint 1 (4W Development + 1W UT) | TN20231201-18188 | CLM-01L/F : Claim Management Listing and Details Form(Mgmt Portal) | Assign | 2023-Dec-06 | 2023-Dec-14 |  |  | 0 | 0 | 0 | 7 | 0 | 0.00 | 0 | 0.00 | 4 | 2 | task
Java | Thi Ha Naing | Aye Myat Hnin | Than Htoo Aung | Ei Than Thar | DGB-MFI SYSTEM-MA-2023.06.01 | MFI System-Maintenance | TN20231121-18048 | BM Approval Percentage Configuration for ETP loan products [CR-000003] | QAT | 2023-Nov-23 | 2023-Dec-06 | 2023-Nov-28 |  | 0 | 0 | 0 | 9 | 0 | 100.00 | 80 | 20.00 | 9 | 1 | task
Java | Thiha Phyo | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Edu Goal Product | TN20231120-18041 | Edu goal data binding checking from quotation to proposal submission | Done | 2023-Nov-20 | 2023-Nov-24 | 2023-Nov-20 | 2023-Nov-29 | 0 | 0 | 5 | 5 | 8 | 100.00 | 100 | 0.00 | 2 | 2 | task
Java | Thiha Phyo | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Proposal Module | TN20231122-18067 | Payor Party PDF form | Done | 2023-Nov-22 | 2023-Nov-29 | 2023-Nov-22 | 2023-Dec-04 | 0 | 0 | 5 | 6 | 9 | 100.00 | 100 | 0.00 | 3 | 2 | task
Java | Thiha Phyo | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Proposal Module | TN20231128-18112 | Financial Questionnaire Form | Done | 2023-Nov-28 | 2023-Dec-01 | 2023-Nov-28 | 2023-Dec-04 | 0 | 0 | 3 | 4 | 5 | 100.00 | 100 | 0.00 | 2 | 1 | task
Java | Thiha Phyo | May Lwin Khaing | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Issue | TN20231204-18214 | Betel Review Issue fix | Done | 2023-Dec-04 | 2023-Dec-06 | 2023-Dec-04 | 2023-Dec-05 | 0 | 0 | 0 | 3 | 2 | 100.00 | 100 | 0.00 | 1 | 1 | task
Java | Thiha Phyo | May Lwin Khaing | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Proposal Module | TN20231204-18215 | Signature Insert for PDF file | QAT | 2023-Dec-04 | 2023-Dec-07 | 2023-Dec-05 |  | 0 | 0 | 0 | 4 | 0 | 75.00 | 80 | -5.00 | 2 | 1 | task
Java | Zin Min Thant | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Internal Mobile Unit 2022 | Sprint 4 (6 Weeks - Dev + User Review) | TN20231116-17970 | Jenkin installation for Testing Server | Done | 2023-Nov-17 | 2023-Nov-20 | 2023-Dec-04 | 2023-Dec-04 | 0 | 0 | 14 | 2 | 1 | 100.00 | 100 | 0.00 | 1 | 1 | task
Mobile | Arkar Nyein | Nwe Yi Win | Sei Thu Win | Sei Thu Win | KACE: KBZMS Automated Claims Essential | Sprint 1 (4W Development + 1W UT) | TN20231129-18144 | ITM-01L-Item Listing | Development | 2023-Dec-01 | 2023-Dec-13 | 2023-Nov-29 |  | 0 | 0 | 0 | 9 | 5 | 46.15 | 50 | -3.85 | 6 | 2 | task
Mobile | HayMan Lawon Htet | Nwe Yi Win | Sei Thu Win | Sei Thu Win | KACE: KBZMS Automated Claims Essential | Sprint 1 (4W Development + 1W UT) | TN20231129-18143 | WSH-01F-Workshop Setup Form | Development | 2023-Dec-01 | 2023-Dec-13 | 2023-Nov-29 |  | 0 | 0 | 0 | 9 | 5 | 46.15 | 50 | -3.85 | 6 | 2 | task
Mobile | KHANT TI KYI | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Sprint 4 (6 Weeks - Dev + User Review) | TN20231121-18054 | Task Reply API Integration | Done | 2023-Nov-21 | 2023-Nov-24 | 2023-Nov-21 | 2023-Nov-29 | 0 | 0 | 5 | 4 | 7 | 100.00 | 100 | 0.00 | 1 | 2 | task
Mobile | KHANT TI KYI | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Sprint 4 (6 Weeks - Dev + User Review) | TN20231121-18056 | Proposal Edit + Signature remove | Done | 2023-Nov-22 | 2023-Nov-28 | 2023-Nov-22 | 2023-Dec-04 | 0 | 0 | 6 | 5 | 9 | 100.00 | 100 | 0.00 | 1 | 2 | task
Mobile | KHANT TI KYI | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Sprint 4 (6 Weeks - Dev + User Review) | TN20231122-18073 | Calendar UI + add task to calendar | Done | 2023-Nov-23 | 2023-Nov-30 | 2023-Nov-23 | 2023-Dec-04 | 0 | 0 | 4 | 6 | 8 | 100.00 | 100 | 0.00 | 2 | 3 | task
Mobile | KHANT TI KYI | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Issue | TN20231124-18093 | Proposal back button routing mapping | Done | 2023-Nov-24 | 2023-Nov-30 | 2023-Nov-26 | 2023-Nov-29 | 0 | 0 | 0 | 5 | 3 | 100.00 | 100 | 0.00 | 1 | 2 | task
Mobile | KHANT TI KYI | May Lwin Khaing | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Sprint 4 (6 Weeks - Dev + User Review) | TN20231129-18154 | Issue fix | QAT | 2023-Nov-29 | 2023-Dec-07 | 2023-Nov-29 |  | 0 | 0 | 0 | 7 | 6 | 88.89 | 83 | 5.89 | 5 | 2 | issue
Mobile | Myo Min Ko | Nwe Yi Win | Sei Thu Win | Sei Thu Win | KACE: KBZMS Automated Claims Essential | Sprint 1 (4W Development + 1W UT) | TN20231129-18145 | ITM-01F-Item Setup Form | Development | 2023-Dec-01 | 2023-Dec-13 | 2023-Nov-29 |  | 0 | 0 | 0 | 9 | 5 | 46.15 | 60 | -13.85 | 6 | 2 | task
Mobile | Shwe Sin Nyein | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Proposal Module | TN20231122-18066 | Life Pro Application PDF form | Done | 2023-Nov-22 | 2023-Nov-29 | 2023-Nov-24 | 2023-Nov-29 | 0 | 0 | 0 | 6 | 4 | 100.00 | 100 | 0.00 | 4 | 1 | task
Mobile | Shwe Sin Nyein | Kaung Thant Kyaw | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Sprint 4 (6 Weeks - Dev + User Review) | TN20231128-18137 | life pro application pdf form checkbox fix | Done | 2023-Nov-28 | 2023-Dec-01 | 2023-Nov-28 | 2023-Dec-01 | 0 | 0 | 0 | 4 | 4 | 100.00 | 100 | 0.00 | 2 | 1 | issue
Mobile | Shwe Sin Nyein | May Lwin Khaing | May Myat Mon | Zin Wuityee Htun | Digital Square-Mobile Application for DLMM | Proposal Module | TN20231204-18225 | Active Care PDF binding | QAT | 2023-Dec-04 | 2023-Dec-08 | 2023-Dec-04 |  | 0 | 0 | 0 | 5 | 2 | 60.00 | 85 | -25.00 | 2 | 1 | task
Mobile | Thein Naing Oo | Aye Myat Hnin | Kaung Htet Kyaw | Kaung Htet Kyaw | Anastas XBITU | New Requirement develop requested from Training Session | TN20231128-18105 | Develop Multi Devices Process for login (Email verify) | Task Complete | 2023-Nov-28 | 2023-Dec-04 | 2023-Nov-28 |  | 0 | 0 | 2 | 5 | 0 | 100.00 | 90 | 10.00 | 4 | 1 | task
Mobile | Thein Naing Oo | Aye Myat Hnin | Kaung Htet Kyaw | Kaung Htet Kyaw | Anastas XBITU | New Requirement develop requested from Training Session | TN20231129-18163 | Develop Wallet external transfer status "waithdraw fail " | Done | 2023-Nov-29 | 2023-Dec-01 | 2023-Nov-30 | 2023-Dec-01 | 0 | 0 | 0 | 3 | 2 | 100.00 | 100 | 0.00 | 2 | 1 | task
Mobile | Thein Naing Oo | Aye Myat Hnin | Kaung Htet Kyaw | Kaung Htet Kyaw | Anastas XBITU | New Requirement develop requested from Training Session | TN20231204-18204 | Develop new device request process | Development | 2023-Dec-04 | 2023-Dec-11 | 2023-Dec-04 |  | 0 | 0 | 0 | 6 | 0 | 37.50 | 40 | -2.50 | 5 | 1 | task
Mobile | Thein Naing Oo | Nwe Yi Win | Than Htoo Aung | Ei Than Thar | BNK-AGENT APP(MA)-2022.10.01 | BNK-AGENT APP MAINTENANCE | TN20231204-18211 | BNK SUM App (IOS Version) Error [TS-000508] | QAT | 2023-Dec-05 | 2023-Dec-06 | 2023-Dec-05 |  | 0 | 0 | 0 | 2 | 0 | 100.00 | 80 | 20.00 | 1 | 1 | task
Mobile | Win Lai Shwe Yee Thant | Nwe Yi Win | Sei Thu Win | Sei Thu Win | KACE: KBZMS Automated Claims Essential | Sprint 1 (4W Development + 1W UT) | TN20231129-18142 | WSH-01L-Workshop Listing | Development | 2023-Dec-01 | 2023-Dec-13 | 2023-Nov-29 |  | 0 | 0 | 0 | 9 | 4 | 46.15 | 50 | -3.85 | 6 | 2 | task
QAT | Kaung Thant Kyaw | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Sprint 4 (6 Weeks - Dev + User Review) | TN20231129-18138 | Draft Test Script Preparation | Done | 2023-Nov-29 | 2023-Dec-04 | 2023-Nov-29 | 2023-Dec-04 | 1 | 0 | 0 | 4 | 4 | 100.00 | 100 | 0.00 | 1 | 2 | task
QAT | May Lwin Khaing | May Lwin Khaing | Kaung Htet Kyaw | Kaung Htet Kyaw | New GLPI | Sprint 2 Testing Stage | TN20231120-18021 | Testing for Sprint 2 release | Done | 2023-Nov-20 | 2023-Dec-01 | 2023-Nov-20 | 2023-Dec-01 | 0 | 0 | 0 | 10 | 10 | 100.00 | 100 | 0.00 | 10 | 1 | other
QAT | May Lwin Khaing | May Lwin Khaing | Kaung Htet Kyaw | Kaung Htet Kyaw | New GLPI | Sprint 2 Testing Stage | TN20231128-18109 | Follow Up Development release and prepare testscript for reports | Done | 2023-Nov-28 | 2023-Dec-01 | 2023-Nov-28 | 2023-Dec-01 | 0 | 0 | 0 | 4 | 4 | 100.00 | 100 | 0.00 | 4 | 1 | other
QAT | May Lwin Khaing | May Lwin Khaing | Kaung Htet Kyaw | Kaung Htet Kyaw | New GLPI | Sprint 2 Testing Stage | TN20231204-18207 | Follow up feedback issues and test sprint 2 release | Development | 2023-Dec-04 | 2023-Dec-08 | 2023-Dec-04 |  | 0 | 0 | 0 | 5 | 0 | 60.00 | 30 | 30.00 | 5 | 1 | other
QAT | Nwe Yi Win | Nwe Yi Win | Sei Thu Win | Sei Thu Win | KACE: KBZMS Automated Claims Essential | Sprint 1 (4W Development + 1W UT) | TN20231204-18201 | Test Script : User Management & Role Management | Task Complete | 2023-Dec-04 | 2023-Dec-06 | 2023-Dec-04 |  | 0 | 0 | 0 | 3 | 0 | 100.00 | 90 | 10.00 | 1 | 1 | task
QAT | Nwe Yi Win | Nwe Yi Win | Sei Thu Win | Sei Thu Win | KACE: KBZMS Automated Claims Essential | Sprint 1 (4W Development + 1W UT) | TN20231204-18202 | Test Script : Workshop and Item Management | QAT | 2023-Dec-05 | 2023-Dec-07 | 2023-Dec-04 |  | 0 | 0 | 0 | 3 | 0 | 66.67 | 80 | -13.33 | 1 | 1 | task
R&D | Naing Ye Aung | Aye Myat Hnin | Kaung Htet Kyaw | Kaung Htet Kyaw | Anastas XBITU | New Requirement develop requested from Training Session | TN20231128-18107 | Support Production Testing and Discuss issues | Development | 2023-Nov-28 | 2023-Dec-11 | 2023-Nov-28 |  | 0 | 0 | 0 | 10 | 0 | 64.29 | 70 | -5.71 | 9 | 1 | task
R&D | Naing Ye Aung | Nwe Yi Win | Seng Htoi Pan | Seng Htoi Pan | Lead-Corp Mobile Loan | Sprint 1 & 2 | TN20231128-18136 | LIM002_3 UI - Loan Details (Branch Inquiry) | Done | 2023-Nov-28 | 2023-Dec-04 | 2023-Nov-28 | 2023-Dec-01 | 0 | 0 | 0 | 5 | 4 | 100.00 | 100 | 0.00 | 2 | 2 | task
R&D | Naing Ye Aung | Nwe Yi Win | Seng Htoi Pan | Seng Htoi Pan | Lead-Corp Mobile Loan | Sprint 1 & 2 | TN20231128-18135 | LIM002_1 UI - Loan Details (Normal Status) | Done | 2023-Nov-28 | 2023-Dec-04 | 2023-Nov-28 | 2023-Dec-01 | 0 | 0 | 0 | 5 | 4 | 100.00 | 100 | 0.00 | 2 | 2 | task
R&D | Naing Ye Aung | Nwe Yi Win | Seng Htoi Pan | Seng Htoi Pan | Lead-Corp Mobile Loan | Sprint 1 & 2 | TN20231128-18133 | LIM001_2 UI - Loan List | Done | 2023-Nov-28 | 2023-Dec-04 | 2023-Nov-28 | 2023-Dec-01 | 0 | 0 | 0 | 5 | 4 | 100.00 | 100 | 0.00 | 2 | 2 | task
R&D | Naing Ye Aung | Nwe Yi Win | Seng Htoi Pan | Seng Htoi Pan | Lead-Corp Mobile Loan | Sprint 1 & 2 | TN20231128-18128 | LIM001_1 UI - Loan Status(If doesn't have) | Done | 2023-Nov-28 | 2023-Dec-04 | 2023-Nov-28 | 2023-Dec-01 | 0 | 0 | 0 | 5 | 4 | 100.00 | 100 | 0.00 | 2 | 2 | task
R&D | Naing Ye Aung | Nwe Yi Win | Seng Htoi Pan | Seng Htoi Pan | Lead-Corp Mobile Loan | Sprint 1 & 2 | TN20231128-18127 | MPM001 UI - My Page | Done | 2023-Nov-28 | 2023-Dec-04 | 2023-Nov-28 | 2023-Dec-01 | 0 | 0 | 0 | 5 | 4 | 100.00 | 100 | 0.00 | 2 | 2 | task
QAT | Aye Myat Hnin |  | Kaung Htet Kyaw |  | Anastas XBITU | Transition Stage | TN20231128-18106 | Test Multi Devices login process from Dev Team | Done | 2023-Nov-28 | 2023-Dec-01 | 2023-Nov-28 | 2023-Dec-01 | 0 | 0 | 0 | 4 | 4 | 100.00 | 100 | 0.00 | 4 | 1 | ba_task
QAT | Kaung Thant Kyaw | Kaung Thant Kyaw | May Myat Mon | May Myat Mon | Digital Square-Mobile Application for DLMM | Sprint 4 (6 Weeks - Dev + User Review) | TN20231129-18138 | Draft Test Script Preparation | Done | 2023-Nov-29 | 2023-Dec-04 | 2023-Nov-29 | 2023-Dec-04 | 1 | 0 | 0 | 4 | 4 | 100.00 | 100 | 0.00 | 1 | 2 | task
QAT | May Lwin Khaing | May Lwin Khaing | Kaung Htet Kyaw | Kaung Htet Kyaw | New GLPI | Sprint 2 Testing Stage | TN20231120-18021 | Testing for Sprint 2 release | Done | 2023-Nov-20 | 2023-Dec-01 | 2023-Nov-20 | 2023-Dec-01 | 0 | 0 | 0 | 10 | 10 | 100.00 | 100 | 0.00 | 10 | 1 | other
QAT | May Lwin Khaing | May Lwin Khaing | Kaung Htet Kyaw | Kaung Htet Kyaw | New GLPI | Sprint 2 Testing Stage | TN20231128-18109 | Follow Up Development release and prepare testscript for reports | Done | 2023-Nov-28 | 2023-Dec-01 | 2023-Nov-28 | 2023-Dec-01 | 0 | 0 | 0 | 4 | 4 | 100.00 | 100 | 0.00 | 4 | 1 | other
QAT | May Lwin Khaing | May Lwin Khaing | Kaung Htet Kyaw | Kaung Htet Kyaw | New GLPI | Sprint 2 Testing Stage | TN20231204-18207 | Follow up feedback issues and test sprint 2 release | Development | 2023-Dec-04 | 2023-Dec-08 | 2023-Dec-04 |  | 0 | 0 | 0 | 5 | 0 | 60.00 | 30 | 30.00 | 5 | 1 | other
QAT | Nwe Yi Win | Nwe Yi Win | Sei Thu Win | Sei Thu Win | KACE: KBZMS Automated Claims Essential | Sprint 1 (4W Development + 1W UT) | TN20231204-18201 | Test Script : User Management & Role Management | Task Complete | 2023-Dec-04 | 2023-Dec-06 | 2023-Dec-04 |  | 0 | 0 | 0 | 3 | 0 | 100.00 | 90 | 10.00 | 1 | 1 | task
QAT | Nwe Yi Win | Nwe Yi Win | Sei Thu Win | Sei Thu Win | KACE: KBZMS Automated Claims Essential | Sprint 1 (4W Development + 1W UT) | TN20231204-18202 | Test Script : Workshop and Item Management | QAT | 2023-Dec-05 | 2023-Dec-07 | 2023-Dec-04 |  | 0 | 0 | 0 | 3 | 0 | 66.67 | 80 | -13.33 | 1 | 1 | task
QAT | Yin Nyein Kyaw |  | Hnin Pwint Phyu Khine |  | Internal QAT Unit 2023 | Learning Tasks | TN20231128-18129 | To Learn Appium iOS Automation | Done | 2023-Nov-28 | 2023-Dec-01 | 2023-Nov-28 | 2023-Dec-01 | 0 | 0 | 0 | 4 | 4 | 100.00 | 100 | 0.00 | 4 | 1 | ba_task
QAT | Yin Nyein Kyaw |  | Wint Thandar Oo |  | Internal QAT Unit 2023 | Learning Tasks | TN20231204-18212 | To study Appium | Task Complete | 2023-Dec-04 | 2023-Dec-05 | 2023-Dec-04 |  | 0 | 0 | 1 | 2 | 0 | 100.00 | 90 | 10.00 | 2 | 1 | ba_task
QAT | Yin Nyein Kyaw |  | Wint Thandar Oo |  | Internal QAT Unit 2023 | Learning Tasks | TN20231205-18233 | IOS App Testing with Appium | Development | 2023-Dec-06 | 2023-Dec-08 | 2023-Dec-05 |  | 0 | 0 | 0 | 3 | 0 | 0.00 | 62 | -62.00 | 3 | 1 | ba_task

## Individual Summary
Task Owner
Name | Ongoing | Complete | Overdue Task Count | Total DEV Overdue Days | Total DEV Workload | Overdue Rate | Progress Achievement | Warning | Compliment
Aye Myat Hnin | 0 | 1 | 0 | 0 | 4 | 0 | 90 | 0 | 0
Kaung Thant Kyaw | 0 | 1 | 0 | 1 | 1 | 1 | 90 | 0 | 0
May Lwin Khaing | 1 | 2 | 0 | 0 | 19 | 0 | 210 | 0 | 0
Nwe Yi Win | 2 | 0 | 0 | 0 | 2 | 0 | 170 | 0 | 0
Yin Nyein Kyaw | 2 | 1 | 0 | 0 | 9 | 0 | 182 | 0 | 0
Aye Myat Hnin | Nov 29 | Nov 30 | Dec 01 | Dec 02 | Dec 03 | Dec 04 | Dec 05 | Dec 06 | Total Overdue Rate
Overdue Task Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Task Count | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Daily Overdue Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kaung Thant Kyaw | Nov 29 | Nov 30 | Dec 01 | Dec 02 | Dec 03 | Dec 04 | Dec 05 | Dec 06 | Total Overdue Rate
Overdue Task Count | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Task Count | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Daily Overdue Rate | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
May Lwin Khaing | Nov 29 | Nov 30 | Dec 01 | Dec 02 | Dec 03 | Dec 04 | Dec 05 | Dec 06 | Total Overdue Rate
Overdue Task Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Task Count | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1
Daily Overdue Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Nwe Yi Win | Nov 29 | Nov 30 | Dec 01 | Dec 02 | Dec 03 | Dec 04 | Dec 05 | Dec 06 | Total Overdue Rate
Overdue Task Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Task Count | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0
Daily Overdue Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yin Nyein Kyaw | Nov 29 | Nov 30 | Dec 01 | Dec 02 | Dec 03 | Dec 04 | Dec 05 | Dec 06 | Total Overdue Rate
Overdue Task Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Task Count | 1 | 1 | 1 | 0 | 0 | 1 | 2 | 1
Daily Overdue Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tester
Name | Ongoing | Complete | Overdue Task Count(Ongoing) | Total QAT Overdue Days | Total QAT Workload | Overdue Rate | Progress Achievement | Warning | Compliment
Aye Myat Hnin | 15 | 9 | 0 | 0 | 26 | 0 | 150 | 0 | 0
Kaung Thant Kyaw | 19 | 13 | 0 | 0 | 49 | 0 | 260 | 0 | 0
May Lwin Khaing | 11 | 7 | 0 | 0 | 21 | 0 | 408 | 0 | 0
Nwe Yi Win | 12 | 11 | 0 | 0 | 40 | 0 | 270 | 0 | 0
Yin Nyein Kyaw | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aye Myat Hnin | Nov 29 | Nov 30 | Dec 01 | Dec 02 | Dec 03 | Dec 04 | Dec 05 | Dec 06 | Total Overdue Rate
Overdue Task Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Task Count | 4 | 6 | 7 | 4 | 4 | 6 | 5 | 3
Daily Overdue Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kaung Thant Kyaw | Nov 29 | Nov 30 | Dec 01 | Dec 02 | Dec 03 | Dec 04 | Dec 05 | Dec 06 | Total Overdue Rate
Overdue Task Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Task Count | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0
Daily Overdue Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
May Lwin Khaing | Nov 29 | Nov 30 | Dec 01 | Dec 02 | Dec 03 | Dec 04 | Dec 05 | Dec 06 | Total Overdue Rate
Overdue Task Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Task Count | 2 | 3 | 4 | 3 | 3 | 6 | 7 | 4
Daily Overdue Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Nwe Yi Win | Nov 29 | Nov 30 | Dec 01 | Dec 02 | Dec 03 | Dec 04 | Dec 05 | Dec 06 | Total Overdue Rate
Overdue Task Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Task Count | 6 | 6 | 6 | 0 | 0 | 1 | 3 | 2
Daily Overdue Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yin Nyein Kyaw | Nov 29 | Nov 30 | Dec 01 | Dec 02 | Dec 03 | Dec 04 | Dec 05 | Dec 06 | Total Overdue Rate
Overdue Task Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Task Count | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daily Overdue Rate | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## QA Daily Task Summary
Dept/Team | Staff | Date | On Leave | Not Accepted | On-going Tasks | QAT Tasks | Review Tasks | Complete Tasks | Done Tasks | Task Status Updated | Task Progress Updated | Total Progress Achived
QAT | Aye Myat Hnin | 2023-11-29 | No | 0 | 1 | 2 | 0 | 1 | 3 | 2 | 3 | 40.0 %
QAT | Aye Myat Hnin | 2023-11-30 | No | 0 | 1 | 3 | 0 | 1 | 3 | 3 | 4 | 60.0 %
QAT | Aye Myat Hnin | 2023-12-01 | No | 0 | 1 | 4 | 0 | 3 | 2 | 4 | 4 | 70.0 %
QAT | Aye Myat Hnin | 2023-12-02 | No | 0 | 1 | 4 | 0 | 3 | 0 | 0 | 0 | 0.0 %
QAT | Aye Myat Hnin | 2023-12-03 | No | 0 | 1 | 4 | 0 | 3 | 0 | 0 | 0 | 0.0 %
QAT | Aye Myat Hnin | 2023-12-04 | No | 0 | 0 | 2 | 0 | 4 | 3 | 4 | 4 | 40.0 %
QAT | Aye Myat Hnin | 2023-12-05 | No | 0 | 0 | 3 | 0 | 6 | 1 | 2 | 2 | 20.0 %
QAT | Kaung Thant Kyaw | 2023-11-29 | No | 0 | 1 | 2 | 0 | 1 | 6 | 9 | 7 | 70.0 %
QAT | Kaung Thant Kyaw | 2023-11-30 | No | 0 | 1 | 2 | 0 | 0 | 1 | 3 | 2 | 60.0 %
QAT | Kaung Thant Kyaw | 2023-12-01 | No | 0 | 1 | 0 | 0 | 5 | 1 | 6 | 5 | 110.0 %
QAT | Kaung Thant Kyaw | 2023-12-02 | No | 0 | 1 | 0 | 0 | 5 | 0 | 0 | 0 | 0.0 %
QAT | Kaung Thant Kyaw | 2023-12-03 | No | 0 | 1 | 0 | 0 | 5 | 0 | 0 | 0 | 0.0 %
QAT | Kaung Thant Kyaw | 2023-12-04 | No | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0.0 % | Resign
QAT | Kaung Thant Kyaw | 2023-12-05 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 % | Resign
QAT | May Lwin Khaing | 2023-11-29 | No | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 7 | 53.0 %
QAT | May Lwin Khaing | 2023-11-30 | No | 0 | 2 | 1 | 0 | 2 | 0 | 2 | 6 | 67.0 %
QAT | May Lwin Khaing | 2023-12-01 | No | 0 | 2 | 3 | 0 | 4 | 1 | 3 | 4 | 45.0 %
QAT | May Lwin Khaing | 2023-12-02 | No | 0 | 2 | 3 | 0 | 4 | 0 | 0 | 0 | 0.0 %
QAT | May Lwin Khaing | 2023-12-03 | No | 0 | 2 | 3 | 0 | 4 | 0 | 0 | 0 | 0.0 %
QAT | May Lwin Khaing | 2023-12-04 | No | 0 | 1 | 3 | 0 | 2 | 5 | 4 | 4 | 90.0 %
QAT | May Lwin Khaing | 2023-12-05 | No | 0 | 1 | 4 | 0 | 4 | 1 | 3 | 8 | 78.0 %
QAT | Nwe Yi Win | 2023-11-29 | No | 0 | 0 | 5 | 0 | 1 | 3 | 1 | 2 | 15.0 %
QAT | Nwe Yi Win | 2023-11-30 | No | 0 | 0 | 6 | 0 | 1 | 0 | 0 | 4 | 13.0 %
QAT | Nwe Yi Win | 2023-12-01 | No | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 6 | 37.0 %
QAT | Nwe Yi Win | 2023-12-02 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 %
QAT | Nwe Yi Win | 2023-12-03 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 %
QAT | Nwe Yi Win | 2023-12-04 | No | 0 | 1 | 1 | 0 | 0 | 0 | 4 | 2 | 110.0 %
QAT | Nwe Yi Win | 2023-12-05 | No | 0 | 2 | 2 | 0 | 1 | 0 | 3 | 2 | 60.0 %
QAT | Yin Nyein Kyaw | 2023-11-29 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 10.0 %
QAT | Yin Nyein Kyaw | 2023-11-30 | No | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 15.0 %
QAT | Yin Nyein Kyaw | 2023-12-01 | No | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 35.0 %
QAT | Yin Nyein Kyaw | 2023-12-02 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 %
QAT | Yin Nyein Kyaw | 2023-12-03 | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0 %
QAT | Yin Nyein Kyaw | 2023-12-04 | No | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 60.0 %
QAT | Yin Nyein Kyaw | 2023-12-05 | No | 0 | 1 | 0 | 0 | 1 | 0 | 2 | 2 | 32.0 %